MIG - Municipal Infrastructure Grant

Guideline Document –

NATIONAL MIG MANAGEMENT UNIT PROGRAMME MANAGEMENT PROCESSES AND PROCEDURES

Revision 2 – 10 September 2004

Note: The processes and procedures are flexible depending on the existence of PMU’s and capacity in municipalities. This is a working document and will be revised as and when required.

CONTENTS

1.	Introduction	5

2.	Principles and objectives of the Municipal Infrastructure Grant	5

2.1	Key principles	5

2.2	MIG Grant objectives	7

3.	Institutional Arrangements	7

3.1	At Municipal sphere – the devolution of Responsibility to the lowest level	7

3.2	At Provincial Sphere	8

3.3	ResponsibilitY Matrix	8

4.	Conditions applied to the MIG	18

4.1	Principles relating to the setting of conditions	18

4.1.1	Division of Revenue Act	18

4.1.2	Cross-cutting conditions	18

4.1.3	Sector specific conditions	20

5.	Communication flow and Control procedures	21

5.1	Interaction	21

5.1.1	Interaction between the National MIG Management Unit, Provincial Programme Management Unit, PMUs and Municipalities	21

5.1.2	Interaction between PMU, Municipality and project consultant/s	21

5.2	Meetings	22

5.2.1	Progress Meetings	22

5.2.2	Quarterly Workshops	23

5.2.3	Ad-hoc Meetings / Site Visits	23

6.	Generic reporting mechanisms, formats and procedures	24

6.1	Division of Revenue Act – Monthly reporting	24

6.1.1	Recipient Municipalities	25

6.1.2	PMUs	25

6.1.3	Provincial Programme Management Unit	25

6.1.4	National MIG Management Unit	26

6.1.5	dplg – Chief Financial Officer	26

6.2	Monthly Progress Report	27

6.2.1	Recipient Municipalities	27

6.2.2	PMU	28

6.2.3	Provincial Programme Management Unit	28

6.2.4	National MIG Management Unit	28

6.3	KPI Report	29

6.4	ANNUAL REPORT	30

7.	MIG national fund administration system	30

7.1	Provincial Project Management Capacity	Error! Bookmark not defined.

7.2	Municipal Infrastructure Grant (MIG)	31

7.2.1	Recipient Municipalities	31

7.2.2	PMUs	31

7.2.3	Provincial Programme MIG Management Unit	33

7.2.4	National MIG Management Unit	33

7.2.5	Under spending at municipal level	34

7.2.6	Control measures for expenditures/transfers	34

7.2.7	Assist municipalities	34

7.2.8	Delaying of payments	35

7.2.9	Withholding of payments	35

7.2.10	Non-compliance	35

7.3	RE-ALLOCATION OF MIG FUNDS	35

8.	MIG management information system  (MIS)	35

8.1	Preliminary Phase	35

8.1.1	Project Registration Form	36

8.2	Pre-implementation Phase (Design & Tender)	37

8.2.1	Register consultant	37

8.2.2	Request for payment (Design phase)	37

8.3	Implementation phase (Construction)	37

8.3.1	Register contractor	37

8.3.2	Request for Payment (Construction phase)	39

8.3.3	Physical Completion Report	39

8.3.4	Request for Payment (Retention)	39

9.	General Filing and backup Procedures	39

9.1	Backups	39

9.2	Project Files	39

9.3	Minutes	40

9.4	Reports	40

9.5	Financial Administration System	40

9.5.1	Request for Draw downs	40

9.5.2	Proof of Expenditure (1084’s)	40

9.6	Service Level Agreements	41

ABBREVIATIONS

The following abbreviations are used throughout this document.

BAS  	:	Basic Accounting System

CETA	: 	Construction for Education Authority

DME	:	Department of Minerals and Energy

DoH	:	Department of Housing

DORA  	:	Division of Revenue Act

DoT	:	Department of Transport

DPLG	:	Department of Provincial and Local Government

DPW	:	Department of Public Works

DWAF  	:	Department of Water Affairs and Forestry

EMM  	:	Executive Manager MIG

EPWP	:	Expanded Public Works Programme

GIS	:	Geographical Information System

IDP	:	Integrated Development Plan

IIF	:	Infrastructure Investment Framework

IT	:	Information Technology

KPIs  	:	Key Performance Indicators

LGCB	:	Local Government Capacity Building Grant

LIC	:	Labour Intensive Construction

MIIF	:	Municipal Infrastructure Investment Framework

MIS	:	Management Information System

MITT  	:	Municipal Infrastructure Task Team

NQF	:	National Qualification Framework (SETA – Sector for Education Training Authority)

O&M	:	Operation and Maintenance

PMITT  	:	Provincial Municipal Infrastructure Task Team

PMM  	:	Provincial Manager MIG

PPMU	:	Provincial Programme Management Unit

PMU  	:	Project Management Unit

SMF  	:	Senior Manager Finance

SMIF  	:	Special Municipal Infrastructure Fund

SMM  	:	Senior Manager MIG

SMME  	:	Small, Medium and Micro Enterprises

## Introduction

The purpose of this guideline document is to create conformity and to regulate the MIG programme management processes and procedures.

The national MIG management unit’s main responsibility is the administration of MIG funds and therefore will have to implement the following management processes and procedures across all spheres of government:

- Communication, documentation and information flows generic to all sectors and departmental policies

- Generic reporting mechanism, formats and procedures

- MIG national fund administration system

- MIG management information system (MIS).

The planning process of Municipal Infrastructure Investment is not covered in this document as planning is addressed at a Macro level by the MIIF and Micro level by municipalities during the development of the Integrated Development Plans (IDP’s).

This document is a working / live document and will be updated as and when the environment / conditions changes.

## Principles and objectives of the Municipal Infrastructure Grant

### Key principles

The Municipal Infrastructure Grant will complement the introduction of the equitable share for local government, although it will not be provided unconditionally to municipalities. The key principles underpinning the design of the MIG are outlined below:

a)	Focus on infrastructure required for a basic level of service:  The MIG programme is aimed at providing only basic infrastructure.

b)	Targeting the poor:  The programme is aimed at providing services to the poor and funds will therefore be targeted to reach them.

c)	Maximising economic benefits:  The programme will be managed to ensure that the local economic spin-offs through providing infrastructure are maximised.  This includes employment creation and the development of enterprises.

d)	Equity in the allocation and use of funds:  The mechanism for distributing funds must provide for equitable access to such funds by the poor in order to make uniform progress in closing the infrastructure gap.

e)	Decentralisation of spending authority within national standards:  Decisions relating to the prioritisation of municipal infrastructure spending, such as the identification, selection and approval of projects, are best undertaken at municipal level, with the following provisions:

- the operating finance and management arrangements must be in place;

- a degree of national and provincial influence over capital spending, expressed through clear norms, standards and spending conditions must be retained; and

- unintended consequences should be limited: the grant must promote sound management practices, not the reverse.

f)	Efficient use of funds:  Funding must be used to provide the greatest possible improvement in access to basic services at the lowest possible cost. This implies the following:

- There should be an appropriate selection of service levels.

- Incentives and conditions must ensure that other funds are mixed with grant funds to minimise leakage to non-eligible households and service levels.

- The mechanism to disburse funds should be simple and easy to monitor, and the outcomes of municipal spending should be easy to evaluate.

g)	Reinforcing local, provincial and national development objectives:  This implies the following:

- The funding mechanism must be consistent with the planning processes of local, provincial and national government.

- Nodal municipalities associated with the Urban Renewal Strategy and the Integrated Sustainable Rural Development Programme must receive proportionally greater allocations of funding.

- Spatial integration must be promoted.

- The emphasis placed on the selection of appropriate service levels.

- The formula should promote appropriate municipal performance relative to policy objectives.

- Predictability and transparency:  Funds should be provided to individual municipalities on a three-year basis, consistent with medium term budgeting practice, with minimal in-year changes and with year to year changes based only on clearly defined conditions. It is also essential for municipalities and other stakeholders to easily understand how the funds are distributed.

### MIG Grant objectives

National government provides infrastructure subsidies to ensure that all households have access to a basic level of infrastructure services. The benefits of this intervention are well known, particularly in relation to the public good characteristics of many municipal services.

In the context of the principles outlined above, the key objectives of the Municipal Infrastructure Grant are to:

a)	fully subsidise the capital costs of providing basic services to poor households: this implies that priority must be given to meeting the basic infrastructure needs of poor households, through the provision of appropriate bulk, connector and internal infrastructure in key services;

b)	distribute funding for municipal infrastructure in an equitable, transparent and efficient manner, which supports a co-ordinated approach to local development and maximises developmental outcomes;

c)	assist in enhancing the developmental capacity of municipalities, through supporting multi-year planning and budgeting systems; and

d)	provide a mechanism for the co-ordinated pursuit of national policy priorities with regard to basic municipal infrastructure programmes, while avoiding the duplication and inefficiency associated with sectorally fragmented grants.

## Institutional Arrangements

### At Municipal sphere – the devolution of Responsibility to the lowest level

The MIG is a conditional grant to municipalities, and thus the management of the grant at municipal level must occur within the planning, budgeting, financial management and operational arrangements in this sphere. Effective management and utilisation of capital funding, falls within the responsibility of the municipal manager.

Government, through the MIG programme, will therefore assist municipalities in the development of appropriate capital programme management capacity, typically achieved through the establishment of project management units (PMUs) within municipalities. PMUs will be accountable to the council and management structure of the municipality in which they are established. However, they will be supported and monitored by the national MIG unit and by the Provincial Programme Management Units.

Effective area-based, service sector and project planning is central to the success of a municipality’s infrastructure investment programme. The MIG programme promotes the creation of an enabling environment through the devolution of responsibility to the lowest possible level and has two dimensions:

- devolution of the project management function, which implies the establishment of a PMU within a municipality to ensure that there is ‘sufficient capacity’ to undertake the function.

- devolution of responsibility for control of the funds, with associated accounting responsibility and the requirement to contract with consultants and contractors, with the associated legal implications.

### At Provincial Sphere

All national departments and their provincial counterparts retain their policy making and regulatory functions which cover the full range of municipal activity: governance, administration, planning, projects and operations. Furthermore, the departments and provinces retain their constitutional right to intervene directly in the affairs of municipalities.  (Reference: Constitution of RSA Act 108 of 1996)

Within the context of the MIG strategies, the provincial departments, through the provincial programme management units, will continue to hold responsibility for supporting and developing appropriate municipal planning capabilities. The MIG programme will integrate with these sectoral planning initiatives through ensuring that:

- The MIG programme is properly integrated with municipal IDPs;

- Planning for regional scale infrastructure is guided by provincial government, working in conjunction with the municipalities and their PMUs;

- The municipal PMUs are supported in their function of overseeing project feasibility studies within the municipalities they serve, as part of the municipal planning process.

The following matrix details the specific roles, functions and responsibilities of each sphere of government.

### ResponsibilitY Matrix

The role and responsibilities of the various role-players are as follows:

| M MUNICIPAL SPHERE – Including Project Management Units (PMU) |  |  |  |
| --- | --- | --- | --- |
|  | Outputs | Activities | Indicators |
|  | Financial Management: | - The PMU is responsible for the administration and financial management of MIG funds, within the municipal and national accounting systems for infrastructure projects of the municipality and any other municipalities where the PMU has been delegated this authority. - The PMU is responsible for the compliance of all conditions contained in the Division of Revenue Act framework (DORA) relating to all funding mechanisms. - The PMU is directly responsible for the reconciliation and timely submission of all DORA reporting and adhoc reporting as and when required. - Final compilation of monthly, quarterly, bi-annual and annual reports to the MIG Manager - Monitor the consolidated cash flow performance reports on each projects and on the regional programme collectively - Verify and reconcile quarterly transfers from National to the DMs and LMs - Audit and administer the monthly claims and expenditure | - DORA reports - Municipal financial reports |
|  | Project Identification and Prioritisation | - The co-ordination of the project identification and prioritisation process for municipalities served by the PMU, whilst ensuring proper integration of the respective IIF’s and IDP’s with the appropriate input from the various other government line function departments to ensure synchronised service delivery. - Ensure that municipalities have the resources to operate and maintain the project throughout the project lifecycle. - Ensure that municipalities budget for the capital replacement or rehabilitation costs thereafter. - The feasibility process necessitates that due consideration be given to the feasibility of the project in terms of: - Provincial and regional growth strategies - Integrated regional-level infrastructure planning and technical feasibility of the projects. - Infrastructure backlog studies. - Labour Intensive Projects (EPWP Guidelines for labour intensive construction). | - IDP - Sector Plans - Provincial / Regional Infrastructure investment plans - Backlog studies - Contribution to Labour Intensive Projects (EPWP) |
|  | Special Municipal Infrastructure Fund | - The co-ordination of SMIF project applications; in support of innovation in the provision of infrastructure - Also in terms of cost effective regional-level infrastructure solutions involving a number of municipalities. | - SMIF Business Plans - Regional Infrastructure Investment plan - Technical studies supporting innovation |
|  | Programme / Project Management: | The PMU will be responsible for the management of the local infrastructure programme (municipal scale) as well as physical project implementation activities while ensuring that: - all projects meet overall planning objectives and specific key performance indicators as determined by the MIG Unit. - the co-ordination of regular progress meetings at local level and representation at the national progress meetings. - the associated project management administrative functions from project registration, evaluation through to final project completion reports. - Project manage the labour-intensive projects in line withy the EPWP framework and the related reporting requirements - Conduct site-visits / meetings to ensure compliance to the Project Registration form and the Letter of Acceptance. - Manage cash flows and committed project expenditure | - Minutes of meetings - Site visit reports - Labour Intensive reports - Cash flow reports |

| MUNICIPAL SPHERE – Including Project Management Units (PMU) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Outputs | Activities |  |  | Indicators |
|  | Monitoring Database: | - The PMU will be responsible for the (IT) management of the monitoring database and the preparation of all necessary reports to municipal and the relevant provincial and national departments. - Generation of Registration forms/ Business plans / Feasibility studies - Data capture, updating and replication of all data and KPIs |  |  | - National MIG Information System (MIS) |
|  | Administration / Contract Administration | - The co-ordination of SMIF project applications; in support of innovation in the provision of infrastructure - Also in terms of cost effective regional-level infrastructure solutions involving a number of municipalities. - Audit compliance of legal conditions, required from the different spheres and sectors of Government - Maintenance of site visit reports, OH&S register |  |  | - Contract Documentation for consulting engineers and contractors - MOAs etc |
|  | Other Capital Works Funding | - Capital works funded from other sources will be included within the competence of the PMU. - Labour Intensive Projects (EPWP) – Encourage the use of the EPWP Guidelines for labour intensive construction. |  |  |  |
|  | Project –based Capacity Building | - The PMU will be responsible for the broad co-ordination of project-based capacity building and developmental initiatives. - This capacity building component of MIG is only concerned with projects and the arrangements relating to the effective delivery of municipal infrastructure and will be targeted in the following manner: |  |  | - Capacity Building Plans - Community awareness campaigns. - SMME Learnerships - Worker training during employment - Employment exist strategies - Training Programmes - Municipal Partnerships (SMME) - Community Based Partnerships - Community Based Partnerships |
|  |  | Scale of Initiative | Type of Activity | Key Features |  |
|  |  | Project Level | Project Implementation | Capacity building is associated with improving the ability of communities to become involved with the project planning and construction of projects. With regard to the latter the focus is on labour-based construction and small contractor development |  |
|  |  |  | Operational | Under this category the project includes an undertaking to train the future services provider (or operator) to operate the infrastructure. Typically this would involve community-based organisations but it may also be aimed at municipal staff. In some cases the obligation to support services providers may extend for up to three years. Such costs may be included under project costs. |  |
|  |  | Programme level) Municipal Scale | Programme Management | The focus of the national effort under the national MIG office will be on building the capacity of project management units (PMUs) to ensure that they can fulfil their functions. |  |
|  |  |  | Project Implementation | There may be a local motivation to establish programme scale initiatives, which could include district scale labour-based construction programmes, particularly for roads. Such initiatives typically have a strong capacity building element. |  |

| MUNICIPAL SPHERE – Including Project Management Units (PMU) |  |  |  |
| --- | --- | --- | --- |
|  | Outputs | Activities | Indicators |
|  | Operation and Planned Maintenance | - Municipal Infrastructure Investment Planning together with Integrated Development Planning is necessary for long-term financial sustainability of municipal assets. In support of this, it is critical that municipalities have planned maintenance programmes for their assets on one hand and the resources and capacity on the other. - It is the responsibility of the PMU to ensure that the municipality has the resources to fulfil the operations and maintenance obligations for all capital projects. The PMU will assist wherever possible with regard to the planning and implementation of the O&M programmes, directly or indirectly. | - Operation and Planned Maintenance Programme - Updated asset registers (GIS based) |
|  | GIS | - The GIS functions would be based at the provincial offices. The GIS function can be also be based at the PMU's and where the GIS is based at Province, municipalities can make use of those provincial facilities. | - GIS database - Asset registers |
|  | Project Monitoring and Evaluation | - Socio-economic impact assessments detailing how the MIG programme has impacted on the communities and municipalities in terms of; skills development, community involvement, employment creation, training, municipal partnerships, local economic development and how the lives of the communities have improved. - Facilitation of backlog studies and environmental impact assessments of projects when necessary. | - Impact Assessment Reports - Backlog studies - Monthly Reports |
|  | Community Liaison / Development / communications | - It is critical to the success of the programme that there is the appropriate communication and liaison with the community in respect of project planning and implementation to ensure buy-in and long term sustainability of the projects in terms of the community understanding the need to pay for services as well as the development of community-based partnerships for the purposes of O&M as discussed above under the point project-based capacity building. - Facilitate community liaison linkages to ensure full community participation at all stages of a project’s life cycle. - Develop and implement a communication strategy in line with provincial and national objectives - Press releases - Co-ordinate opening and hand over ceremonies - MIG orientation workshops etc - Prepare and develop MIG capacity building business plan in alignment with the municipal Local Government Capacity Building Programme (LGCBG). - Co-ordinate the project-based capacity building in terms of: - job creation, with the focus on introducing labour-based construction methodology and the development of SMMEs where technically feasible. - the development community-based partnerships for the operation and maintenance of the infrastructure. - Monitor and report on implemented capacity building initiatives. | - Community liaison checklists - Training schedules |

| PROVINCIAL SPHERE – Provincial Programme Management Unit (PPMU) |  |  |  |
| --- | --- | --- | --- |
|  | Outputs | Activities | Indicators |
| 1 | Planning / Developmental Initiatives | Establishment of MIG structures: - Develop Provincial MIG Management Business Plan - Setup / establish Provincial MIG Management unit - Support and facilitate the establishment of the municipal Project Management Units (PMU) Infrastructure Investment Planning: - Ensure that municipal IDPs combine to form a viable development framework across the province, and are vertically integrated with the Provincial Growth and Development Strategy - Support the determination of municipal backlogs and the provision GIS systems to support the planning process - Ensure that IDPs give priority to the basic needs of communities and promote the social and economic development of communities - Ensure through the IDP process - the prioritization of residential infrastructure for water, sanitation, electricity, refuse removal, streets, housing connector, and other municipal infrastructure like roads, in line with any MIG or sector policies established before the start of the municipal financial year - Support and monitor municipalities to prepare and implement Water Services Development Plans (WSDP’s) – in cooperation with DWAF - Ensure proper co-ordination between all municipal infrastructure programmes within the respective province - Build capacity of municipalities to ensure the development of a three-year capital plan linked to its IDP and budget - approval by the municipal council required no later than 30 June 2004. Asset Management: - Build capacity of municipalities to ensure the development of a sustainable operational and maintenance programme for the three years and beyond – the cost of which is reflected within the approved three-year capital plan budget. - Build capacity of municipalities to ensure the development of a sustainable operational and maintenance programme of existing infrastructure for water, sanitation, electricity and other infrastructure – and associated budget. - GIS systems support for the development of an efficient and sustainable asset management programme. Local Economic Development / Capacity Building: - Support the establishment of municipal service partnerships through the MIG programme - Facilitate the implementation of labour-intensive methods in accordance with the EPWP Guidelines for labour intensive construction and the SETA Learnership Programme. - Approval of municipal capacity building business plans, which must include community based partnerships etc. | - Minutes of meetings - Evaluation reports of IDPs - Three year capital plan (Municipal) - Provincial Growth and Development Strategy - Partnership agreements |
| 2 | Facilitation with other Provincial Sector Departments. Liaison with National Departments: | - Establishment of Provincial Municipal Infrastructure Task Team (PMITT) - All sector departments participate within scope of the Provincial Municipal Infrastructure Task Team (PMITT) - Establishment of Provincial Municipal Infrastructure Technical Task Team (MIT3) - Coordination between all sector departments - Scheduled Meetings - Regular progress meetings with PMUs (chaired by PMU manager) - Report back monthly meetings with the representative of the National MIG Unit, Provincial Programme Management Unit (PPMU), the PMU managers and Sector departments - Quarterly workshops with the representative of the National MIG Unit. | - Minutes of meetings |

| PROVINCIAL SPHERE – Provincial MIG Management Unit (PMMU) |  |  |  |
| --- | --- | --- | --- |
|  | Outputs | Activities | Indicators |
| 3 | Monitoring and Evaluation | Central the role of provinces is the building of institutional capacity of the municipalities to ensure the effective delivery of municipal infrastructure. Financial management: - Provincial treasuries must monitor municipal capital budgets, and the reporting on expenditure, while each provincial sector department will be expected to fulfill sectoral monitoring role. - Monitoring the financial status of municipalities through Project Viability - Monitor compliance with DORA framework Performance: - Projects registered only when in compliance with MIG criteria. - Progress meetings with PMUs in terms of cash flows, KPIs, etc - Monitor programme performance reports (DORA reports, MIG monthly reports, MIG quarterly reports, labour intensive reports, O&M reports) which would include some of the following indicators: - Monthly cashflow performance management - Achievement of MIG KPIs. - Achievement of LIC KPIs. - Bi-annual reports - O&M budgetary constraints - Monitor ‘M’ factor - Monitor performance of municipalities in terms of; expenditure, the DORA framework and compliance to grant conditions - Progress on removal of backlogs Administration / Legal Compliance: - Legal agreement compliance by implementing control mechanisms and guidelines - Procurement procedures - MOA conditions in alignment with grant conditions - Update and maintain national data information system at provincial and municipal level. Extended functions: - Ensure adherence to the labour-intensive construction methods in terms of the Expanded Public Works Programme (EPWP) guidelines agreed between Department of Public Works, National Treasury and SALGA, for at least low-volume roads, sidewalks, storm-water drainage, trenching etc. - Ensure that Labour Intensive Projects (EPWP) can be distinguished from non- Labour Intensive Projects (EPWP). - Monitor capacity constraints/ gaps - Monitor the outputs of the municipal operation and maintenance programmes - Monitor the adherence of Occupational Health and Safety plans - Project implementation progress monitoring with site meetings - Register of site visit reports | - Project viability audit reports - Minutes of meetings, Progress reports - Performance monthly reports - Site visit reports - EPWP report - O&M reports - OH&S plans / audits - Site visit reports |

| PROVINCIAL SPHERE – Provincial MIG Management Unit (PMMU) |  |  |  |
| --- | --- | --- | --- |
|  | Outputs | Activities | Indicators |
| 4 | Communication | - MIG awareness campaigns at municipal level, orientation workshops, technical workshops etc - MIG brochures, handouts newsletters etc - Media Implementation awareness articles, press releases etc - Maintain a photographic data base of projects and events - Input for MIG website | - Media material - Website |
| 5 | Capacity Building / technical support / | - Promoting the development of local government capacity to enable municipalities to perform their MIG function. - Facilitate the building of institutional capacity in terms of: - Project management - Infrastructure investment planning - Financial management of capital budgets - Procurement procedures (Compliance with CIDB registration conditions) - Legal / contractual - OH&S requirements - Labour-Intensive design and methodology - Asset Management - MIS data base - operation and maintenance - MIG administration and reporting systems - Impact assessments - Provide GIS systems support to the planning process as well as the in the development of an efficient and sustainable asset management programme. - Facilitate the development of municipal Occupational Health and Safety plans not only in terms of project implementation but also with respect to operation and maintenance procedures. | - Training schedules - GIS database - OH&S reports |
| 7 | Intervention | All national departments and their provincial counterparts retain their policy making and regulatory functions which cover the full range of municipal activity: governance, administration, planning, projects and operations. Furthermore, the departments and provinces retain their constitutional rights to intervene directly in the affairs of municipalities. The Municipal Systems Act also states the following: The MEC for local government in a province must establish mechanisms, processes and procedures in terms of s 155 (6) of the Constitution to: - Monitor municipalities in the province in managing their own affairs, exercising their powers and performing their functions - Monitor the development of local government capacity in the province. - Assess the support needed by municipalities to strengthen their capacity to manage their own affairs, exercise their powers and perform their functions. With the above in mind, intervention would be required in the following circumstances: - Non performance of municipalities in terms of expenditure (‘M’ factor) - Non-compliance with MIG conditions and crosscutting conditions as detailed in section 8 of MIG policy framework - Non-compliance: project scope, mismanagement, misappropriation of funds, improper procurement procedures, with reporting requirements etc | Reference: The Constitution of the Republic of South Africa. Section 139, section 154 (1), section 155 (6) and section 155 (7). Reference was also made to the Municipal Systems Act - section 105 (1)(a) and section 105 (1) (b)&(c) |

| NATIONAL SPHERE |  |  |  |
| --- | --- | --- | --- |
|  | Outputs | Activities | Indicators |
| DEPARTMENT OF PROVINCIAL AND LOCAL GOVERNMENT |  |  |  |
|  | Overarching DPLG outputs | - Exercises financial accountability for the MIG programme. - Administration of grant transfers. - Setting up of the restructured MITT, chairing the MITT and its technical committee (MIT3) and providing them with the secretariat function. - Setting up the MIG Unit - Compile an annual report to parliament on the MIG programme. - Monitor performance in respect of generic conditions. - Responsible for monitoring the cross-cutting conditions |  |
| NATIONAL MIG MANAGEMENT UNIT |  |  |  |
|  | Primary Functions | Administering the use of MIG funds (ensuring that the funds are properly allocated and spent on appropriate projects). This activity relates only to the way projects are implemented and implies that national and provincial government departments retain their normal responsibilities for policy, regulation and capacity building relating to municipal governance, administration, planning and operations activities. Functions include the following: - Implementing policy relating to infrastructure delivery; - Setting up a the MIG national fund administration system, including monitoring arrangements; - Ensuring the establishment of project management units in selected municipalities - Operating the national MIG information system; - Monitoring the use of MIG funds; - Auditing the local programmes to ensure compliance; - Ensuring that evaluation of local programmes takes place; and - Preparing reports to MITT and to provincial and national government departments. |  |
| MUNICIPAL INFRASTRUCTURE TASK TEAM (MITT) |  |  |  |
|  | Overall Functions: | All national departments and their provincial counterparts retain their policy making and regulatory functions which cover the full range of municipal activity: governance, administration, planning, projects and operations. Furthermore, the departments and provinces retain their constitutional rights to intervene directly in the affairs of municipalities. However, the importance of co-ordinating such activity, with the objective of creating a common approach to local government, is recognised. The Municipal Infrastructure Task Team (MITT) has therefore been established and assigned these co-ordinating functions. The MITT will have the following overall functions: - To review municipal infrastructure policy to ensure efficiency, effectiveness and consistency in the delivery of infrastructure by municipalities; - To monitor progress and unblock any challenges that may emerge in the delivery of services; and - To make decisions on the above. |  |

|  | Outputs | Activities | Indicators |
| --- | --- | --- | --- |
|  | Policy Reviews | - Reflect and review municipal infrastructure policy as and when required; - Review emerging developments emanating from other programmes and process which have direct bearing on municipal infrastructure delivery e.g. the restructuring of electricity distribution industry; - Review sector service delivery targets; - Promote financial, technical, social and environmental sustainability; - Make policy proposals to Cabinet; - Monitor sector service delivery impact; - Agree on regulations, where required; - Propose scaling down or broadening the scope of service delivery levels, where required; and - Ensure the fulfilment of commitments emanating from the decisions of the Cabinet Makgotla, Clusters and Local Government MinMec. |  |
| TECHNICAL MITT (MIT3) |  |  |  |
|  | Overall Functions | The MITT will be supported by the technical MITT, which is referred to as MIT3. This will be formed from the same departments as the MITT, with representatives at Chief Director level or their mandated alternates. SALGA and the national MIG programme manager will also serve on the team. The MIT3 will report directly to the MITT and will have the following responsibilities: - Ensure that the MITT agenda focuses on the sectoral priorities; - Determine sectoral priorities, which are linked, to Departmental objectives; - Facilitate implementation of the Municipal Infrastructure Grant (MIG) policy; - Promote financial, technical, social and environmental sustainability of municipal services through infrastructure programmes. - Monitor and ensure implementation of MIG; - Assess and monitor the progress made by Departments in implementing the decisions taken at the MITT meetings; - Ensure that sufficient information needed for a decision is collected; - Oversee the implementation of the pilot projects; - Facilitate the establishment of the MIG unit; - Coordinate the implementation of the MIG; - Draft policy amendments and other expert advise to the MITT; - Coordinate the reviews of the MIIF document; - Oversee the work of Working Committees - Commission studies on infrastructure. - Coordinate impact studies on the MIG. - Review and correct blockages in process. - Ensure proper co-ordination between sector departments. - Review regular reports from municipalities and PMU’s. - Recommend policy changes to the DG/higher committee. - Review Sector reports. |  |

| OTHER NATIONAL DEPARTMENTS |  |  |  |
| --- | --- | --- | --- |
|  | Outputs | Activities | Indicators |
|  | National Treasury (NT) | - Administers legislation that has implications for the MIG programme, notably DORA. - Incorporation of MIG conditions and transfers into DORA. - Ensure that municipalities observe and operate within the macroeconomic framework driven by national - government. |  |
|  | Department of Water Affairs and Forestry (DWAF) | - Policymaking, including the setting of norms and standards for water services infrastructure. - Planning oversight (regional and water service development plans). - Monitoring of water sector related conditions and progress in meeting targets. - Initiating intervention related to water services activities. |  |
|  | Department of Public Works (DPW) | - Coordinate the Expanded Public Works Programme - Set criteria related to poverty alleviation and employment generation. - Advise municipalities on intensive labour-based processes, systems, techniques and approaches. - Liaise with municipalities on procurement reforms. - Monitor performance in relation to employment generation, labour based technology and SMME involvement. |  |
|  | Department of Minerals and Energy (DME) | - DME's responsibilities will relate initially to policy development. Once the Integrated National Electrification Programme (INEP), has been incorporated into the MIG programme it will undertake similar responsibilities to those identified for DWAF. |  |
|  | Department of Transport (DoT) | - Policy relating to municipal roads and municipal transport. - Monitoring of the performance of municipalities in the provision of roads and compliance with conditions applicable to this sector. - Ensuring that funds allocated to transport infrastructure are properly spent. |  |
|  | Department of Housing (DoH) | - Coordination of policy and planning of housing development and the provision of infrastructure through the MIG programme. - Synchronisation between the MIG programme and the Housing Fund. |  |
|  | Department of Labour (DoL) | Training of workers on Labour Intensive Projects (EPWP). |  |
|  | Department of Sport and Recreation South Africa (DSRSA) | - Policy relating to sports and recreation. - Ensuring that MIG funds are properly applied to building associated infrastructure. - Monitor conditions applicable to this sector. |  |

## Conditions applied to the MIG

The MIG is a conditional grant. The formula is intended to allocate funding in accordance with government’s policy priorities. The utilisation of this funding in accordance with these policy priorities and objectives is a function of the conditions imposed on its use by beneficiary municipalities.

### Principles relating to the setting of conditions

Conditions will be applied to ensure that municipalities appropriately address the objectives and parameters of this policy statement. The conditions seek to avoid placing an undue burden of compliance on municipalities. Therefore, the number of conditions must not be excessive and it must be possible to easily measure performance in relation to the conditions.

The following conditions will be applicable on the MIG Programme:

- Division of Revenue Act

- Cross-cutting conditions

- Sector specific conditions

#### Division of Revenue Act

Refer to the Division of Revenue Act for the current financial.

Refer to the relevant Conditional Grant Frameworks in the DORA:

- Municipal Infrastructure Grant (MIG).

#### Cross-cutting conditions

The following conditions (Section 8.2 of the MIG policy framework document, Concise version – final dated 5 February 2004) are set as the founding conditions for the MIG programme, which may be varied from time to time by the MITT. The PMU must ensure compliance with these conditions:

- Conformity with IDPs: No MIG funds may be spent outside the framework of a municipality’s pre-existing Integrated Development Plan and its approved budget. The IDPs should be based on the provision of a basic package of services to the poor, appropriate services levels, financial sustainability and the existence of adequate organisational capacity.

- Limitation on operational spending: The MIG grant can only be used for capital investment and cannot be used to finance operating expenditure other than the prescribed percentage permitted for the operation of a project management unit in applicable municipalities.

- Restrictions on eligibility: Spending of MIG funds is restricted to those categories of infrastructure, beneficiaries and levels of service identified in Section 5 of the MIG Policy Document. To ensure that eligibility requirements are met a cap on capital spending per household will be set and specific requirements may be set for the amount of spending on particular types of infrastructure.

- Adequate attention to rehabilitation: The municipality must invest an appropriate proportion of the funds on rehabilitating existing infrastructure.

- Pledging of funds to secure loan finance: No ‘pledging’ (the assigning of capital grant funds to be used to pay off a loan to a particular lending organisation) may be undertaken with MIG funds.

- Achievement of specified basic service coverage targets: the attainment of pre-agreed basic service coverage targets in specific sectors (water and sanitation, for example) to be achieved by a particular municipality over a three-year period, based on their current position.

- Poverty alleviation: It is important for the economic spin-offs of infrastructure delivery to be maximised. This relates primarily to temporary and permanent job creation arising for municipal infrastructure investments. This condition will be associated with national government’s 'Expanded Public Works Programme' (EPWP). The gender provisions of this programme must be adhered to.

- Reporting: The recipient municipality has prepared and submitted all monthly reports on grant utilisation in a prescribed format by a specified time.

- MIG funds to be allocated in municipal budget: All MIG funds to be spent in any year must be allocated to specific projects, which must be identified in municipal budgets.

- Registration of MIG projects (otherwise referred to as project feasibility study): All projects to be funded with MIG funds, wholly or partially, must have a project registration form which conforms with requirements to be established for the MIG programme and which must be registered on the national MIG database before the award of contracts for construction commences.

#### Sector specific conditions

Each sector department (DWAF, DME, DoT and DSRSA) may establish further conditions specific to their sectors. Such conditions will be included at the discretion of the Municipal Infrastructure Task Team.

##### Department of Public Works

To adhere to the labour-intensive construction methods in terms of the Expanded Public Works Programme (EPWP) guidelines agreed between Department of Public Works, National Treasury and SALGA, for at least low-volume roads, sidewalks, storm-water drainage, trenching etc.

##### Department of Water Affairs and Forestry

- The funding is only to be used for the Basic Water Services component of the projects. Basic water services in this case means Basic Water Supply Facilities and/or Basic Sanitation Facilities as defined in the Strategic Framework for Water Services, approved by Cabinet September 2003.

- Projects to be funded must be within the Water Services Development Plan (WSDP) as the Sector Component of the Integrated Development Plan (IDP).

- Projects to be funded must be proven to be viable, feasible, acceptable and sustainable based on a proper feasibility study.

- To ensure sustainable operation and maintenance of the proposed infrastructure the operating, finance and management arrangements must be in place and committed. (If acceptable to the other sectors, this could be a crosscutting condition).

- Projects must be implemented in line with the policies as set by the Strategic Framework for Water Services and the legal requirements of the Water Services Act (Act 108 of 1997) as well as the National Water Act (Act 36 of 1998).

##### Department of Transport

The development of road infrastructure to poor households that would create access to trade, local economic development and essential services and to promote road safety.

## Communication flow and Control procedures

Overall, control of the MIG programme can only be exercised effectively if processes and procedures and proper communication lines are followed:

### Interaction

#### Interaction between the National MIG Management Unit, Provincial MIG Management Unit, PMUs and Municipalities

- All communication from the National MIG Management Unit will be via the Provincial MIG Management Units as indicated on the Institutional Management flowchart.

- The National MIG Management Unit can only communicate directly with the Municipalities on financial matters (disbursement of funds, etc), with a copy of the summary of the discussion submitted to the Provincial Programme Management Unit.

#### Interaction between PMU, Municipality and project consultant/s

The PMU and project consultant/s will communicate to each other via the Municipality where a PMU is not located within a municipality.

### Meetings

In order for the National MIG Management Unit to conduct its primary and overall functions (refer to Item 4.3 – Responsibilities matrix) and to monitor the compliance of crosscutting and sector specific conditions as well as progress, the following meetings are envisaged:

#### Progress Meetings

This meeting will be between the National MIG and Provincial Programme Management Units as well as the PMUs.

| Chairperson | : | To alternate between the four Senior Managers (dplg) |
| --- | --- | --- |
| Co-ordinator | : | dplg delegated official; |
| Intervals | : | Monthly |
| Dates | : | Meeting schedule to be provided by National MIG Management Unit |
| Venue | : | Provincial Programme Management Unit’s offices |
| Attendance | : | National MIG Management Unit, Provincial Programme Management Units and relevant PMUs. |
| Purpose | : | To monitor: - overall progress (financial, project implementation) - compliance of MIG conditions - achievement of specified KPIs - the establishment of PMUs - Labour intensive projects - Nodal municipalities - Special Municipal Infrastructure Fund (SMIF) - Infrastructure categories and funding elements - Three-year development plans (submission & compliance) To discuss: - project registrations, MIS and IT related matters - administrative matters - auditing requirements - policy issues - financial matters - communication - reporting formats/requirements - problems experienced and possible solutions / suggestions |
| Agenda | : | See appendix B for an example of a draft Agenda. |

The National MIG Management Unit will be responsible to compile, finalize and distribute the minutes of the monthly meetings within 7 working days after the date of the meeting to all relevant parties.

The progress meeting’s agenda must be distributed to all the relevant parties at least 7 working days before the meeting.

#### Quarterly Workshops

| Chairperson | : | dplg delegate |
| --- | --- | --- |
| Co-ordinator | : | dplg delegate |
| Intervals | : | Quarterly |
| Dates | : | Meeting schedule to be provided by National MIG Management Unit |
| Venue | : | To be determined (alternating between nine provinces) |
| Attendance | : | National MIG Management Unit (Senior Managers) and nine (9) Provincial Programme Management Units. Representatives of Sector Departments could be invited. |
| Purpose | : | - Report on progress during previous 3 months - Report on “best practices” / labour intensive projects - Strategic planning between all role-players - Provincial feedback on issues/matters that could hamper the implementation of the programme - Discuss new innovation projects - Information, transformation and way forward - Presentations by private/public sector specialist on key issues - Team building exercise. |
| Agenda | : | See appendix B for an example of a draft Agenda. |

The National MIG Management Unit will be responsible to compile, finalize and distribute the minutes of the quarterly workshop within 22 working days after the date of the workshop to all relevant parties.

The quarterly workshop’s agenda must be distributed to all relevant parties at least 14 working days before the workshop.

#### Ad-hoc Meetings

These meetings will be conducted by the National MIG Management Unit , in conjunction with the Provincial MIG Management Unit’s members, to obtain grass-root level information on specific projects and/or to intervene/resolve problem areas at PMUs, Municipalities and/or projects.

## Generic reporting mechanisms, formats and procedures

The reports must be submitted as listed in the table below in order to achieve the required milestone dates.

Note:  The KPI Report must be submitted on a quarterly basis therefore the dates above is relevant to the month in which the report is due.

### Division of Revenue Act – Monthly reporting

The duties of the transferring national officer (dplg – Chief Financial Officer) and receiving officers (municipal managers of recipient municipalities) are clearly stipulated in the yearly Division of Revenue Act.

The monthly DORA report would reflect on the following items:

- the amount of funds transferred / received by a municipality

- the amount of funds delayed or withheld from any municipality and the reasons for such a delay or withholding

- the actual expenditure incurred by the municipality in respect of its allocation

- the extent of compliance by a municipality with the conditions of an allocation and the Division of Revenue Act

- an explanation for any material (supplier) problems experienced or variations effected by a municipality and a summary of the steps taken to deal with such problems or the effect of such variations

- such other issues as the National Treasury may determine.

The procedures and timeframes for the submission of the monthly DORA reports for the various spheres of government are as follows:

#### Recipient Municipalities

The PMU of the recipient municipality shall develop, verify, reconcile, check and submit the hard copy of the monthly DORA report and the updated electronic format (Excel spreadsheet) and a signed hard copy of the DORA report to the relevant Municipal Manager no later than the 3rd of each month.

#### PMUs

The PMU will verify and reconcile the monthly DORA reports received from the municipal managers.  Any discrepancies, errors and/or queries must immediately be forwarded to the municipal manager/s for rectification/clarification.

A consolidated PMU DORA report will be compiled by the PMU and submitted to the PMU manager for approval.

Any discrepancies, errors and/or queries must immediately be forwarded to the Municipal managers for rectification/clarification.

The PMU manager shall submit the updated electronic format (Excel spreadsheet) and a signed hard copy of the DORA report to the Provincial MIG Management Unit no later than the 6th of each month.

#### Provincial Programme Management Unit

The Provincial Programme Management Unit will verify and reconcile the monthly DORA reports received from the various PMUs in the province.  Any discrepancies, errors and/or queries must immediately be forwarded to the PMU manager/s for rectification/clarification.

A consolidated provincial DORA report will be compiled by the Provincial MIG Management Unit and submitted to the PMM for approval.

The PPMU shall submit the updated electronic format (Excel spreadsheet) and a signed hard copy of the DORA report to the National MIG Management Unit no later than the 10th of each month.

The PPMU must also ensure that an updated electronic format (Excel spreadsheet) and a signed hard copy of the DORA report for the provincial project management capacity for MIG be submitted to the National MIG Management Unit later than the 10th of each month.

Note: The Provincial MIG Management Unit should process reports from the Municipalities as and when they are received.

#### National MIG Management Unit

The National MIG Management Unit will verify and reconcile the monthly DORA reports received from the nine (9) Provincial MIG Management Units.  The monthly DORA reports would be evaluated and verified utilising the following documentation / information:

- Provincial DORA and monthly progress reports (current and previous month)

- dplg’s  BAS system report.

Any discrepancies, errors and/or queries must immediately be forwarded to the Provincial MIG managers for rectification/clarification.

A consolidated national DORA report will be compiled by the National MIG Management Unit and submitted to the Senior Manager Finance (SMF) for approval.

The SMF shall submit an updated electronic format (Excel spreadsheet) and a signed hard copy of the following DORA reports to the EMM no later than the 17th of each month:

- Municipal Infrastructure Grant (MIG)

The EMM shall submit the electronic format (Excel spreadsheet) and a signed copy of the consolidated national DORA reports to the dplg – Chief Financial Officer no later than the 18th of each month.

#### dplg – Chief Financial Officer

The dplg – Chief Financial Officer shall submit the updated electronic format (Excel spreadsheet) and a signed hard copy of the following DORA reports to National Treasury no later than the 20th of each month:

- Municipal Infrastructure Grant (MIG)

### Monthly Progress Report

The National MIG Management Unit must compile and submit a comprehensive monthly progress report to the Executive Manager MIG (EMM) no later than the 20th of each month.  (See Appendix C for the contents of a draft monthly progress report).

The Monthly Progress Report will reflect on the following issues:

| Section 1 : Executive Summary | - Introduction - Financial status - Project implementation status - Programme evaluation - Nodal Municipalities - Labour intensive projects - Special Municipal Infrastructure Fund (SMIF) - Problem areas and remedial action plans by the National and Provincial MIG Management Units. |
| --- | --- |
| Section 2 : Detailed Reports | - Schedule of work - Status of Programme (National perspective) - Project status - Financial status - National cashflow - Provincial cashflows |
| Section 3 : Site visit Reports |  |
| Section 3 : Contact Details |  |

The Monthly Report format and contents must still be finalised.

The procedures and timeframes for the submission of the Monthly Progress Report for the various spheres of government are as follows:

#### Recipient Municipalities

The municipal manager must obtain the completed relevant MIS project forms from the project consultants (see appendix E for example of draft MIS project forms) and submit a signed hard copy of the documentation to the PMU no later than the 3rd of each month.

#### PMU

The PMU must obtain all the updated MIS project forms from the municipalities and capture the information on the MIS.

The PMU manager must evaluate and verify the completeness/correctness of data / information (financial and KPIs) captured on the MIS.  Any discrepancies, errors and / or queries must immediately be forwarded to the Municipal Manager for rectification / clarification.

A consolidated PMU monthly report must be printed from the MIS and a copy, signed by the relevant Municipal manager / authority, will be submitted to the Provincial MIG Management Unit no later than the 6th of each month.

#### Provincial Programme Management Unit

The Provincial Programme Management Unit will generate a consolidated provincial monthly report from the MIS.  The Provincial MIG Management Unit must evaluate and verify this report with the following:

- Monthly report received from the PMUs

- Previous consolidated provincial monthly report

- Previous DORA report received from the PMUs

- Previous consolidated DORA report.

Any discrepancies, errors and / or queries must immediately be forwarded to the PPMU’s for rectification / clarification.

Once the Provincial Manager MIG has approved the consolidated provincial monthly report, the National MIG Management Unit must be notified by no later than the 10th of each month.

#### National MIG Management Unit

The National MIG Management Unit must generate the consolidated national monthly report from the MIS once the Provincial Manager MIG has approved the consolidated provincial monthly report.

The National MIG Management Unit must evaluate and verify this report with the following:

- Previous consolidated national monthly report

- Previous consolidated national DORA report

- The departmental BAS system

Any discrepancies, errors and / or queries must immediately be forwarded to the Provincial MIG Management Unit for rectification / clarification.

The National MIG Management Unit must finalise and submit the report to the EMM for approval no later than the 20th of each month.  Once the report has been approved by the EMM the departmental website will be updated with the relevant report.

### KPI Report

The National MIG Management Unit must compile and submit a KPI report to the EMM on a quarterly basis.  (See Appendix C for the contents of a KPI Report).  This report will be a consolidated report of the previous quarters monthly financial Progress Reports and KPI Report.

The EMM will submit the Quarterly Report to the MITT.  Once the MITT has approved the report, copies will be produced for distribution to the various PMITTs and relevant sector departments and role players.

The KPI Report will reflect on the following:

| Section 1 : Assessment of MIG KPIs | - Summary - Funds allocated to infrastructure categories and funding elements - Implementation in nodal areas - Total financial contributions - Employment opportunities - Women - Youth - Disabled - Number of persons employed - Person days of employment - Training provided per module of training - SMME involvement - Labour intensive projects (EPWP). |
| --- | --- |
| Section 2 : Detailed Reports | - National Report - Provincial Report (nine) |
| Section 3 : Contact Details | - Format and contents still to be finalised. |

The procedures and timeframes for the submission of the Quarterly Report will be exactly as for the monthly progress report except for the fact that it will be compiled on a quarterly basis.

### ANNUAL REPORT

The National MIG Management Unit will compile, on an annual basis, a report on the achievements of the programme in general over the past financial year.  This report will be a consolidated report of:

- The Monthly progress reports

- The four KPI reports

- The two social and economic impact reports

## MIG national fund administration system

The funds for MIG will be appropriated to dplg’s budget and dplg remains overall responsible for the disbursement of funds to provinces and municipalities.

The multi-year formula based allocation will be calculated to provide funds to all Metropolitan and Local Municipal areas.

The allocation, which each municipality will receive, is based on the following parameters:

- Backlogs in specific services

- Poverty

- Identification of a node.

Once the allocations had been gazetted, the EMM will forward a “Letter of Allocation” to the nine provinces and recipient municipalities.

The letters of allocation should at least include information on the following:

- Overview of the MIG programme

- MIG allocation to municipalities

- Requirements of PMUs business plan

- Special Municipal Infrastructure Fund (SMIF)

- Indicative allocations for the remainder of the MTEF period

- Conditions

The dplg would only transfer funds once the recipient municipality has submitted their signed “Certificate of Acceptance and Compliance” in respect of the MIG.

The recipient municipalities must comply with the following conditions stipulated in the DORA framework:

- Prioritise residential infrastructure projects in line with any MIG or sector department’s policies before the start of the municipal financial year

- The Municipal Council must approve their three-year capital plan linked to its IDP and budget no later than 30 June 2004. The budget must reflect the operation and maintenance costs of the three and beyond

- District Municipalities must provide detail information by 30 June 2004 on expected transfers to the local municipalities, as well as any information on projects undertaken directly by the District Municipalities

- All committedments MIG projects must be prioritised

- To adhere to the labour-intensive construction methods in terms of the Expanded Public Works Programme (EPWP) guidelines agreed between the Department of Public Works, National Treasury and SALGA, for at least low-volume roads, sidewalks, stormwater drainage, trenching etc.

- Provide quarterly reports on budget and project implementation.

The funds for the MIG Conditional Grants would be disbursed as follows:

### Municipal Infrastructure Grant (MIG)

Funds would be disbursed by dplg to recipient municipalities according to payment schedule.  MIG funds could only be utilised on projects once the projects are registered and signed-off on the MIS by the SMM in conjunction with the SMF.

#### Recipient Municipalities

The recipient municipalities must compile and submit the following to the PPMU:

- Cover letter from municipal manager

- Certificate of expenditure and revenue signed by the Municipal Manager

- Copies of the proof of payments (1084’s)

- Copies of progress payment certificates of contractors

- Copies of professional fee claims of consultants.

These documents must be submitted to the PMU no later than the 3rd of the month.

It is important to note that the request for drawdown of funds would occur as per the schedule and actual expenditure and proof of payment (1084’s) must be reported on a monthly basis.

#### PMUs

The PPMU will receive and verify the information signed by the municipal managers.  Any discrepancies, errors and/or queries must immediately be forwarded to the municipal manager/s for rectification/clarification. The information must reach the PPMU not later than the 5th of each month.

The PMU manager will receive and verify the information and submit the consolidated draw down, signed by the municipal manager, with supporting documentation and submit to the Provincial MIG Management Unit no later than the 6th of each month.  The PMU manager must also sign the certificates of expenditure and income.

Note: If the Municipality does not have a PMU, the municipality should perform the functions of a PMU, verify and submit all documentation directly to the Provincial MIG Management Unit.

#### Provincial MIG Management Unit

The Provincial MIG Management Unit will verify and reconcile the draw downs received from the various recipient PMUs in the province.  Any discrepancies, errors and/or queries must immediately be forwarded to the PMU project manager/s for rectification/clarification.

A consolidated draw down will be compiled by the Provincial Programme Management Unit and submitted to the PMM for processing. The following documents will be submitted to the National MIG Management Unit not later than the 10th of the month:

- A cover letter from the Provincial MIG Management Unit with a summary of draw downs received from municipalities

- Certificates of expenditure and revenue must also be signed by the PMM.

- Copies of proof of payments (1084’s)

- An updated proof of payment control sheet

(See Appendix D for the relevant forms).

#### National MIG Management Unit

The National MIG Management Unit will receive the consolidated draw down with supporting documentation from the Provincial MIG Management Unit not later than the 10th of the month.  The National MIG Management Unit will then verify and reconcile the information against:

- National monthly progress report

- National monthly DORA report

- dplg’s BAS system

- Updated draw down control sheet on MIS.

The National MIG Management Unit will capture the new information on the MIS hereafter they will compile the following documents for each draw down received and submit it to the SMF, before the 12th of the month, for approval:

- Transfer payment for MIG memorandum

- Sundry payment advice

- The certificate of expenditure and revenue, as compiled and signed by the municipal manager, will be attached.

The National MIG Management Unit will update their proof of payment control sheet and file the copies of the proof of payments received.

The SMF must submit the drawdowns to the EMM for approval.  After approval these documentation must be submitted, no later than the 15th of the month, to the dplg - Financial Administration Department for payment/transfer of funds.

On receipt of proof of transfer of funds from the dplg - Financial Administration Department, the National MIG Management Unit will fax the proof of transfer/s to the Provincial MIG Management Unit as well as recipient municipalities. The draw down control sheet on the MIS will also immediately be updated with latest proof of transfers received.

#### Under spending at municipal level

The National MIG Management Unit will identify, on an ongoing basis, based on monthly reports, any variances/regular/drastic under-expenditure.  The following actions will be taken:

- Confirm the variances with the Provincial MIG Manager

- Write to the municipality within 8 working days after the 10th of the month about the variances explaining the implications thereof and the problems experienced with under expenditure.

- Copy the letter to the Provincial MIG Manager

- Reflect the variances in the monthly Division of Revenue Report

- Write a letter to National Treasury regarding the variances, by the 20th of the month, reflecting the actions taken (such as delaying or withholding of transfers) to address the under-expenditure.

#### Control measures for expenditures/transfers

The National MIG Management Unit transfers funds to municipalities on a monthly drawdown basis.

The Provincial MIG Manager will submit requests for draw downs to the National MIG Management Unit on the 10th of the month where after the National Unit will:

- Assess the expenditure of the municipalities against the transfers.

- Inform the municipalities within 8 working days after the 10th of the month about the variances, explaining the implications thereof and problems experienced with under expenditure.

- If a municipality did not spend 50% of the amount previously transferred the amount still available on their books will be subtracted from their request for drawdown.

- Should a municipality consistently not spend its funds and this situation persists, transfer/payment will be withheld until proof of expenditure and an amended payment schedule are received.

#### Assist municipalities

The National MIG Management Unit will identify municipalities with challenges / problem areas.  Meetings will be arranged with all parties / stakeholders involved (Provincial MIG Manager, municipality, consultant, contractor), to discuss action plans in order to resolve problem areas.  Feedback/follow-up will be necessary to determine if issues have been addressed successfully.

#### Delaying of payments

The National MIG Management Unit will recommend delaying of payments to the National Treasury should provinces/municipalities not comply with the Division of Revenue Act.

#### Withholding of payments

The National Treasury will withhold transfers if the National MIG Management Unit could provide proof of non-compliance with the Division of Revenue Act.

#### Non-compliance

Any serious or persistent non-compliance with the Division of Revenue Act constitutes financial misconduct and dplg would therefore seek National Intervention to attend to these incidents. This includes under-expenditure and non-compliances such as late or no submission of reports or information.  (Also refer to the Local Government: Municipal Finance Management Act and sections 38, 39, 40 and 86 (1) of the Public Finance Management Act).

### RE-ALLOCATION OF MIG FUNDS

Refer to the relevant Division of Revenue Act.

## MIG management information system  (MIS)

Although there will be a number of different information/data capturing forms on the MIS, these forms will follow the logical progressions of a project through its life cycle.  Specific forms have to be completed by the PMUs/Municipalities at certain stages of the project life cycle.

The important benefit with this approach is that only information relevant to the specific phase will be recorded.  Static information from one reporting period to another will also be pre-printed on the forms and the unnecessary capturing of known information will be prevented in this way.

The proposed MIS forms (see Appendix E for examples of each form) that will be used throughout the project life cycle, are as follows:

### Preliminary Phase

See Appendix E for all the relevant forms as specified in the sections below.

#### Project Registration Form

The sector departments must participate in the IDP process.  The project registration form must be completed once the Municipalities and relevant PMU have prioritised the projects to be implemented.  This form will be submitted to the National MIG Management Unit for registration of the project.

The costs involved with the completion of the project registration form, conducting of feasibility studies, value engineering and compilation of technical reports, will be for the account of the recipient municipalities.

Once the project registration form has been signed-off on the MIS system by the SMM and SMF the recipient municipality will be reimbursed for these costs incurred on projects as well as the project cost.

The table below details the method to be followed to ensure the proper evaluation, control and filing of a Project Registration form.

| Evaluation of a project registration form |  |
| --- | --- |
|  | Print replication log from MIS on a daily basis in order to see whether there is any new Project registration forms, additional funding requests or changes. |
|  | Contact PMU requesting whether Project registration form must be evaluated or not. Await confirmation from PMU before proceeding with evaluation. |
|  | Print out Project registration form from MIS. |
|  | Create Project file. |
|  | Check status of project on MIS Check if project is signed off and authorised at PMUl level on MIS Check if project name and number on file correlate with information on MIS Check if all necessary fields on Project registration form is completed Check if project description and motivation correlate and if project qualifies for funding in terms of MIG requirements Check following fields in particular: - Breakdown of funds - Labour Intensive project (EPWP) Yes / No - Average project wage rate - Beneficiaries - Funding (MIG, public and/or private sector) - Employment generation - Women - Youth - Disabled - Number of persons employed - Person days of employment generation - Planned training activities per module of training - Operation and maintenance budget - Outputs and other targets - Budget control - Declaration on standard conditions |
|  | See if the following documentation has been provided by the PMU: - Council Resolution - DWAF Technical Report (only for Water, Sanitation and Waste Disposal projects). |
|  | If above has not been provided, contact PMU requesting this information. Proceed with project registration once all of the documentation has been provided. |
|  | Place project registration form in project file. |
|  | Submit project file to Secretary for information control and tracking. |
|  | Secretary submits files to SMM for sign-off purposes on MIS. |

During evaluation, if found that there is non-compliance to MIG criteria or outstanding information, a letter will be written to the PMU explaining the situation.

This form will be the baseline against which the implementation of the project will be measured (e.g. financial matters, achievement of KPIs and scope of work).

### Pre-implementation Phase (Design & Tender)

#### Register consultant

This form is to be completed once the Municipality has appointed project consultants.

Note:  Consultants appointed on Labour Intensive Projects (EPWP) must take note of the specific requirements according to the SETA NQF qualifications framework for labour-intensive construction, learning guides, learning programmes and assessment instruments.

#### Request for payment from municipality (Design phase)

This form is to be completed at the end of every month during which the project is being designed.

### Implementation phase (Construction)

#### Register contractor

This form is to be completed once the Municipality has appointed the successful tenderer, based on the consultant’s tender evaluation and recommendation.

Note:  Contractors appointed on Labour Intensive Projects (EPWP) must take note of the specific requirements according to the CETA NQF qualifications framework for labour-intensive construction, learning guides, learning programmes and assessment instruments.

#### Request for Payment (Construction phase)

This form is to be completed at the end of every month during which the project is under construction (contractor’s progress certificates and/or consultant professional fee claims).

#### Physical Completion Report

This form is to be completed after the physical completion certificate has been issued (site handover).

#### Request for Payment (Retention)

This form is to be completed when the retention funds of the project become due (expiring of the defect liability period).

## General Filing and backup Procedures

### Backups

This paragraph covers the method to be followed to store backups of computer information.

a)	A backup shall be made at least once every month of all computers in the office and those in the personal possession of each staff member, which contain MIG related information.

b)	Backups shall also be made to the network drive of the dplg at:

Users on 'Pta\Users' (H:)/MIG/Consultants

### Project Files

The National MIG Management Unit must ensure that all documentation relevant to the MIG programme be filed in such a manner so as to enable any member of the Management Unit, to quickly and accurately access any required documentation at any time.

The National MIG Management Unit must keep record of all the projects registered on the MIS and signed-off by the SMM in conjunction with the SMF.

For each project a file must be opened on which the following documentation must be filed and updated on a regular basis:

- Project registration form together with supporting documentation

- Correspondence from sector departments such as DWAF, DPW, DME, DoT, DoH, DSRSA etc.

- DWAF’s response with the regard to the Technical Report submitted

- Certificate of Compliance (DORA)

- General correspondence between the relevant role-players

- Operation and maintenance plan furnished by the municipality

- A copy of the signed (by the Municipal Manager) certificate of fulfilment of conditions together with all relevant / supporting documentation (e.g. Council resolution, agreement between community and municipality on the service package and payment for services, etc).

- Employment records

- Training records

### Minutes

The following documentation must be filed per province:

- Signed copy of the minutes

- Agenda

- Attendance register

- All relevant documentation received at the meeting.

### Reports

The following reports must be filed:

- Monthly progress

- KPI

- Quarterly

- ISRDP & URP

- Monthly DORA

- Ad-hoc reports

### Financial Administration System

#### Submission of Draw downs

The following documentation must be filed in the Provincial Financial file per month:

- Transfer of payment MIG Memorandum

- Sundry payment advice

- Certificate of Expenditure & Revenue (received from PMU)

- Proof of Transfer of funds

- Draw downs control sheet on the MIS

#### Proof of Expenditure (1084’s)

The following documentation must be filed in the Provincial 1084’s file per month:

- Proof of payment control sheet (received from PMU)

- Proof of expenditure.

### Service Level Agreements

The Service Level Agreements between the District Municipalities and Local Municipalities must be filed per province in the Service Level Agreements file.

Municipalities should send letters of acceptance of the MIG conditions on receiving MIG funds.